## Slide 1: Webinar: Risk Management for Oil and Gas Projects
Intaver Institute Inc.
303, 6707, Elbow Drive S.W, Calgary, AB, Canada
Tel: +1(403)692-2252
Fax: +1(403)459-4533
www.intaver.com

## Slide 2: Introduction
Intaver Institute Timeline
  2002: Established
  2004: V.1 RiskyProject
  2009: v 3 Integrated Risk Register
  2012: v 5
RiskyProject
  Full Project Risk Management Lifecycle
  Integrated Risk Register
  Risk Matrix, Risk Planning
  +
  Quantitative Monte Carlo Cost and Schedule Risk Analysis
Clients

## Slide 3: Gorgon Natural Gas Project
Chart: 
| 2003 | 2007 | March, 2009 | September, 2009 | September, 2011, First Phase
 | 11 | 16 | 50 | 34 | 29
Project Cost Estimate in Billions A$
Date of cost estimate
A three-train liquefied natural gas (LNG) facility on Barrow Island (Australia) that will produce 15.6 million metric tons of LNG per year.

## Slide 4: Project Risk Analysis in Portfolio Management Process
Project Cost and Schedule risks and uncertainties
Geological and other Uncertainties affecting production
Price Uncertainties
Other Risks and Uncertainties:
Political risks
Uncertainties in Royalties regimes
….
Economic Analysis of the Projects
Corporate Portfolio Management
Strategic Decision

## Slide 5: Risk Management Affects Project Profitability
Chart: 
| Without risks | With risks | With risks and mitigations
 | 1.8 | 1.8 | 1.8
 | 1.3 | 2.2 | 1.6
Full circle cost of gas
$/Mcf

## Slide 6: Identifying and Managing Critical Risks is Key
Risk
Opportunity?
Threat?

## Slide 7: Which risks are critical?
Risk 3
Risk 4
Risk 1
Risk 5
Risk 2
Risk 1
Risk 2
Risk 3
Risk 4
Risk 5
Schedule risk
Cost Risk
Safety Risk
Legal Risk
Quality Risk
…………….. Risk
Enviromental Risk

## Slide 8: Time is Money: Cost and Schedule Risks
Time Dependent Costs
Cost Risk
Schedule risk drives Costs due to time dependent resource costs
40% -70% cost risk is schedule driven
Schedule risk

## Slide 9
Input 1: Project Schedule
Input 2: List of Risks (Risk Register)
Assign Risks to Project Tasks and Resources
Perform Analysis
Risk Events Approach

## Slide 10: Schedule

## Slide 11: Costs

## Slide 12: Resources
Notes: To model schedule driven cost, we have included high level resources that have been assigned to specific tasks.

## Slide 13: Risk Register

## Slide 14: Risk Assignment
Task | R1 | R2 | R3 | R4 | R5 | R6
Installing Microsoft Seismic monitoring |  |  | x |  | x | 
Deliver frac fleet and install equipment |  |  |  |  | x | 
Deliver rig and equipment |  |  |  |  | x | 
Well 1,2,3 (share common risks) |  |  |  |  | x | 
Rig Mobilization |  |  |  |  | x | 
Drilling | x |  |  | x | x | x
Installing Service Rig |  |  |  |  | x | 
Completion (8 stages fracing) |  | x |  |  | x | 

## Slide 15: Risk Assignment Interface
30 % chance that risk causes a delay and increase in cost of drilling
Risk Assigned to task ‘Drilling’

## Slide 16: Run Monte Carlo Simulation

## Slide 17: Results of Analysis

## Slide 18: Risk Adjusted Project Schedule
Schedule with risks
Schedule without risks
Arrows show risk assignments

## Slide 19: Project Cost
Schedule with risks
Schedule without risks

## Slide 20: Risk Planning – Mitigation Plan

## Slide 21: Pre and Post Mitigation
Pre-mitigation
Post-mitigation

## Slide 22: Risk Planning
Risk: Mechanical Problem with instrument
Post Mitigation $16, 734, 906
Pre-Mitigation Cost 17, 178, 397

## Slide 23: RiskyProject Enterprise
Enterprise Risk Database:
Schedules,
Risks,
Mitigation Plans
RiskyProject Professional
RiskyProject Lite
RiskyProject Risk Register

## Slide 24: Future Reading
Project Think:
Why Good Managers Make Poor Project Choices
Project Decisions: The Art and Science
Introduction to Project Risk Management and Decision Analysis
Project Risk Analysis Made Ridiculously Simple

## Slide 25: Future Reading
P. Leach. 2005. Late and Over Budget: Why Projects Always Seem to Take Longer and Cost More Than Planned. Projects & Profits, Vol. V Issue - XI, November 2005
http://www.project decisions.org
http://www.intaver.com/index-whitepapers.html
http://www.risk-doctor.com/
http://www.projectrisk.com
Contact
Michael Trumper
mtrumper@intaver.com
403.692.2252
Intaver Institute Inc.
www.intaver.com