## Slide 1: Monte Carlo Cost Risk Analysis Reporting
Intaver Institute Inc.
400, 7015, Macleod Trail,
Calgary, AB, Canada
Tel: +1 (403) 692-2252
www.intaver.com
Notes: Welcome to Intaver Institutes video : Monte Carlo Cost Risk Analysis Reporting. We are going to be taking a look at the various analysis and reporting views that are available to assess project cost risk.

## Slide 2: Cost Summary
Cost Histogram and Cumulative Probability
Multiple cumulative probability plots for different baselines
Notes: After running a Monte Carlo simulation, two of the most popular reports are histograms and cumulative probability. In this particular example we have a combined histogram and cumulative probability chart. On the left Y axis is the probability. We can see that the most likely value occurs 9% of the time. On the right Y axis is the cumulative probability values with markers placed at 10 percentile, Mean, and 90 percentile. Cumulative probability is useful for setting cost contingency, which would be the difference between the Deterministic value (the red line) and a cumulative probability with a higher confidence level such as P80.
In addition, we can plot multiple cost scenarios representing different risk management strategies as cumulative probability plots. In this particular view we are looking a a pre and post mitigated baselines.

## Slide 3: Cost Chart
Project Control Indicators
Baseline Cost
Actual Cost
Risked Cost
Notes: The Cost Chart provides a view of the forecasted cost of a project over time for deterministic and risked costs. As we can see, because the project has a high probability of running longer it will cost more. If there are actual costs, they are will be plotted on the chart and project cost control indicators are displayed at the bottom right.

## Slide 4: Cash Flow
Project Cash Flow
Cost for Selected Period of Time
Low
Base
High
Notes: The Cash Flow chart shows probabilistic cash flow over set periodicity (Months, Bi-Monthly, Quarterly or Annually). In this particular view, we can see that for the period of February, there is a high probability that costs will be well above the current forecast due to risk. In addition, we can see that because of delays, the project should expect to experience two additional months of costs.
Because February shows a large jump in expected cash flow, we can take a look a detailed view of the probabilistic cash flow for that particular period. The large spike on the right is due to a probability of a critical risk occuring.

## Slide 5: Sensitivity Analysis
Task Cost Ranking
Risk Cost Ranking
Notes: Sensitivity analysis or Tornado charts provides insight into which tasks or risks have the most potential to drive costs in the project. On the left we have a list of tasks ranked by how much their risks and uncertainties impact the cost of the project. On the right, we have a similar ranking of risks. It is extremely likely that the highest ranked risks are assigned to the highest ranked activities. To minimize potential cost overruns, we need to focus our risk management efforts on these tasks and risks.

## Slide 6: Task: Total Cost vs Variable Cost
Task Total Cost
Task Variable Cost
Notes: In the previous views we have been looking at project level analysis, however, it is possible to drill down to the activity level to view the cost analysis.
On the left, the chart shows us probabilistic total task costs. Of note the histogram is bimodal, which shows two distinct distributions. The one on the left is due to uncertainty or natural variance and the second to the right is due to a serious risk event occurring.
The chart on the right shows similar results but for resource costs. In this chart the second distribution is even more distinct so that we know that the risk is tightly correlated with the resources allocated to this activity.

## Slide 7: Task: Cost per Resource
View Work for Selected Resource
Distribution for Work
Notes: If we would like to further investigate the source, we can look at the specific variable work (and therefore costs) for each resource allocated to a specific tasks. This particular view which is very tightly correlated with the previous results would indicate that in order to control costs, we would need to focus on this particular resource as being the root cause of the predicted cost overruns in this activity.

## Slide 8
White Papers and Articles: http://intaver.com/technology/articles-and-white-papers/
Online Tutorials: http://intaver.com/RiskyProjectTutorial
Risk and Decision Analysis Books: http://www.projectdecisions.org
Contact Details
Michael Trumper
Intaver Institute Inc.
mtrumper@intaver.com
403.692.2252
Additional Resources
Notes: Thank you for watching our video on Monte Carlo Cost Risk Analysis Reporting. Please visit our site at intaver.com to learn more about risk analysis and our upcoming videos and webinars.

## Slide 9: Additional Resources
Project Think:
Why Good Managers Make Poor Project Choices
Project Decisions: The Art and Science
Introduction to Project Risk Management and Decision Analysis
Project Risk Analysis Made Ridiculously Simple
Notes: If you are interested in finding out more about Decision Analysis and Risk Management a list of our publications and a variety of resources can be found at our website Project Decisions.org